# Project Charter Template

| PROJECT NAME |  | PROJECT MANAGERS | Team Name |
| --- | --- | --- | --- |
| Project 5 – Event Management System |  | Amit Sharma Pathan Ahemadasharaf | Group 6 |

PROJECT OVERVIEW

| PROBLEM OR ISSUE | Event organizers confront difficulties handling different event services such as ticketing, payments, scheduling, and attendee involvement with separate systems. This results in inefficiencies, missing opportunities, and a negative participant experience. |
| --- | --- |
| PURPOSE OF PROJECT | “The goal of this project is to design and construct an integrated Event Management System that manages ticketing, registration, reminders, payment processing, advertising, venue navigation, personalized session selection, and networking among attendees”. |
| BUSINESS CASE | We can save administrative time, save operational expenses, and increase revenue from advertising and ticket sales by providing a unified platform for event administration. The project is anticipated to cost $25,000 with an annual benefit of $120,000, for a ROI of more than 80% and a payback period of about 9 months. |
| GOALS / METRICS | - Frictionless sales: ≥ 95% successful payment rate; checkout conversion +15% vs baseline. - Adoption & satisfaction: 5,000+ active attendees in first large event; app rating ≥ 4.5/5; NPS ≥ +30. - Operational efficiency: Reduce onsite check-in time by 50%; cut manual admin hours by 40%. - Engagement: Recommendation CTR ≥ 12%; ≥ 2 meaningful networking connections per attendee on average. - Reliability & speed: P95 page/API latency < 400 ms; uptime ≥ 99.9% during events. |
| EXPECTED DELIVERABLES | - Product requirements & solution design; data model & API specs. - UX/UI prototypes; brand-ready web app + Android/iOS (responsive or hybrid). - Features: ticketing/registration/reminders; payment gateway integration; ad placements & sponsor management; interactive venue map; session recommendation service; attendee profiles/chat/meet-ups. - Admin console (catalog, pricing, promo codes, sponsor inventory, content moderation). - Analytics dashboards (sales funnel, campaign ROI, heatmaps, engagement). - Security & compliance (PCI-DSS scope definition), privacy policy, ToS. - Test plan (unit/integration/load), UAT sign-off, runbooks, training, go-live checklist, support handover. |

PROJECT SCOPE

| WITHIN SCOPE | - Web + mobile (responsive) attendee portal and organizer admin. - Ticket types, promo codes, QR check-in, email/SMS reminders. - Payment processing via a PCI-compliant gateway (e.g., Stripe/Adyen). - Self-serve sponsor ads: placements, targeting, reporting. - Interactive venue map (wayfinding, session rooms, points of interest). - Session recommender (content-based + popularity signals). - Networking: profiles, interests/tags, suggested matches, in-app messages. - Observability (logs/metrics), rate limiting, CDN, WAF. - Training for organizers and help content for attendees. |
| --- | --- |
| - OUTSIDE OF SCOPE | - Native desktop apps; AR indoor navigation; on-prem payments. - 24/7 L1 call center beyond launch month; multi-year vendor management. - Custom hardware turnstiles or badge printers beyond standard QR scanning. - Full multi-language localization beyond EN (phase-2). |

TENTATIVE SCHEDULE

| KEY MILESTONE (note these are examples below and you can choose to put in whatever you like from a Milestone basis) | START | FINISH |
| --- | --- | --- |
| Form Project Team / Preliminary Review / Scope | Oct 08 2025 | Oct 11 2025 |
| Finalize Project Plan / Charter / Kick Off | Oct 12 2025 | Oct 15 2025 |
| Define Phase (optional – choose what you like) | Oct 16 2025 | Oct 25 2025 |
| Planning Phase (optional) | Oct 26 2025 | Nov 03 2025 |
| Executing Phase (optional) | Nov 04 2025 | Dec 6 2025 |
| Project Summary Report and Close Out (optional) | Dec 07 2025 | Dec 20 2025 |

RESOURCES

| PROJECT TEAM | Ahemad Asharaf Pathan (Backend & Project Manager) Amit Sharma (Frontend & UI Developer) Product Manager; Business Analyst; UX/UI Designer; Front-end Devs (2); Back-end Dev; Mobile Dev; Data/ML Engineer; QA Engineer; DevOps/Cloud Engineer; Security Consultant. |
| --- | --- |
| SUPPORT RESOURCES | Cloud services, secure payment gateway, email/SMS APIs, and sponsor data. Payment gateway (PCI-compliant), mapping SDK, email/SMS provider, CDN/WAF, legal/privacy counsel, finance (chargebacks), marketing for ad inventory & sponsors. |
| SPECIAL NEEDS | Venue layout details, reliable internet, and test devices. |

$COSTS

| COST TYPE | VENDOR / LABOR NAMES |  | RATE | QTY | AMOUNT |
| --- | --- | --- | --- | --- | --- |
| Labor (ex Development cost) | Backend Dev |  | $ 50 | 160 hrs | $ 8000 |
| Labor | Frontend Dev |  | $ 45 | 160 hrs | $ 7200 |
| Labor | QA / Tester |  | $ 35 | 80 hrs | $ 2800 |
| Supplies | Cloud hosting, APIs, software licenses |  | $ 35 | 80 hrs | $ 2800 |
| Miscellaneous | Marketing & promotions |  | $ 30 | 50 hrs | $ 1500 |
| Miscellaneous | Design & presentation materials |  | $ 25 | 40 hrs | $ 1000 |
|  |  |  | TOTAL COSTS |  | $ 23,300 |

| TYPE OF BENEFIT (select your own and/or use these) | BASIS OF ESTIMATE |  |  |  | ESTIMATED BENEFIT AMOUNT |
| --- | --- | --- | --- | --- | --- |
| Specific Cost Savings | Reduced manual operations & admin staff hours |  |  |  | $20,000 |
| Enhanced Revenues | Increased ticket sales & advertising revenue |  |  |  | $60,000 |
| Higher Productivity (Soft) | Automated reminders & faster check-ins |  |  |  | $25,000 |
| Improved Compliance | Secured online payments & verified registration |  |  |  | $10.000 |
| Better Decision Making | Data analytics for event optimization |  |  |  | $8,000 |
| Less Maintenance | Retire legacy microsite |  |  |  | $6,000 |
| Other Costs Avoided | Less overtime at entry points |  |  |  | $7,000 |
|  |  |  | TOTAL BENEFIT |  | $136,000 |

Financial Summary / Business Case

| Payback Period, NPV Analysis | - Payback period: ~$23,300 / ($136,000 ÷ 12) ≈ 3 months - Year-1 ROI: (~$136,000 – $23,300) / $136,000 ≈ 82.9% - (Optional) NPV: compute using org’s hurdle rate (e.g., 10%) over 3–5 years. |
| --- | --- |
| Non-financial Considerations | Better attendee experience, stronger sponsor relationships, improved brand perception, scalable foundation for future features (multi-language, AR wayfinding, badge printing). |

RISKS, CONSTRAINTS, AND ASSUMPTIONS

| RISKS | - Payment failures/chargebacks; PCI scope mismanagement. - Traffic spikes during check-in; venue Wi-Fi instability. - Privacy & spam in networking features; abuse/misuse of ads. - Third-party API rate limits (payments, maps, email/SMS). |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CONSTRAINTS | - Fixed budget and ~11-week timeline to align with event date. - Limited on-site staffing; sponsor creative deadlines. |  |  |  |  |  |  |
| ASSUMPTIONS | - Venue provides accurate floor plans & stable internet. - Payment gateway supports local currency & tax rules. - Most attendees on modern mobile devices; email/SMS deliverability acceptable |  |  |  |  |  |  |
| PREPARED BY |  | TITLE |  |  |  | DATE |  |
| Amit Sharma Ahemadasharaf Pathan |  | Project Manager |  |  |  | Oct 04 2025 |  |