# Project Charter: Sustainable Campus Energy & Awareness Project

# Project Title

Sustainable Campus Energy Monitoring & Awareness Initiative

# Project Objective

To improve sustainability practices within the campus by conducting energy audits, implementing real-time energy monitoring systems, and promoting eco-friendly habits among students and staff through technology-enabled solutions and educational campaigns.

# Project Scope

In Scope:
- Energy consumption audit of campus buildings.
- Installation of sensors for real-time energy monitoring.
- Development of dashboards and mobile apps for actionable insights.
- Educational awareness campaigns for students and staff.
- Mock data usage if real-time data is limited.

Out of Scope:
- Large-scale physical infrastructure changes beyond energy monitoring.
- Long-term maintenance post initial implementation.

# Key Deliverables

- Energy consumption audit report
- Real-time energy monitoring dashboard
- Mobile app mock-ups for awareness campaigns
- Educational campaign materials
- Final presentation with actionable insights

# Stakeholders

- Project Sponsor: Campus Administration
- Project Manager: [Your Name / Team Name]
- Technical Team: Data Analysts, Developers, Sensor Installation Team
- End Users: Students, Staff, Sustainability Committee

# Project Timeline (High-Level)

- Week 1–2: Energy Audit & Requirement Gathering
- Week 3–4: Sensor Setup & Data Collection
- Week 5–7: Dashboard and App Development (Mock-ups)
- Week 8–9: Educational Campaign Implementation
- Week 10: Final Review & Presentation

# Project Risks & Assumptions

Risks:
- Delays in sensor procurement.
- Limited student engagement in awareness programs.

Assumptions:
- Campus provides necessary access and approvals.
- Budget covers hardware and software needs.

# Budget (Estimated)

| Item | Estimated Cost (USD) |
| --- | --- |
| Sensors & Installation | $2,000 |
| Dashboard Software | Free (Power BI/Tableau Student) |
| Training & Workshops | $500 |
| Marketing Materials | $300 |

# Success Metrics

- Energy reduction target: 15% in 6 months
- Engagement target: 60% of students/staff using dashboard or app
- Campaign reach: 80% of campus population aware of sustainability practices